## Product_Backlog
Product Name:	Swift Scan
Team ID:	EngiMavs

Name:	Jacob Wilkins
Initials:	JW
Student ID:	1001184498

Name:	Alex Mejia
Initials:	AM
Student ID:

Name:	Zohar Moreno
Initials:	ZM
Student ID:

Name:	Umanga Shrestha
Initials:	US
Student ID:

Name:	Sirjan Khanal
Initials:	SK
Student ID:

Total Features	Left	Available	Completed	Sprint Ends
Total at Start	32	32
Sprint 1	32	32	14	Jul 07
Sprint 2	18	32	14	Jul 14
Sprint 3	18	32	14	Jul 21
Sprint 4	18	32	14	Jul 28
Sprint 5	18	32	14	Aug 04
Sprint 6	18	32	14	Aug 11

Feature ID	Prio	Status	Actual Sprint #		Pts	Cml	I want to...	So that...	Type	Notes
PC1	1	CO			21	21	Complete Section 1 of Product Charter		Doc
PC2	2	CO			13	34	Complete Section 2 of Product Charter		Doc
PC3	3	CO			5	39	Complete Section 3 of Product Charter		Doc
PC4	4	CO			3	42	Complete Section 4 of Product Charter		Doc
PC5	5	CO			3	45	Complete Section 5 of Product Charter		Doc
PC6	6	CO			8	53	Complete Section 6 of Product Charter		Doc
PC7	7	CO			13	66	Complete Section 7 of Product Charter		Doc
PC8	8	CO			3	69	Complete Section 8 of Product Charter		Doc
PC9	9	CO			34	103	Complete Section 9 of Product Charter		Doc
PC10	10	CO			21	124	Complete Section 10 of Product Charter		Doc
PC11	11	CO			8	132	Complete Section 11 of Product Charter		Doc
PC12	12	CO			21	153	Complete Section 13 of Product Charter		Doc
PC13	13	CO			13	166	Complete Section 14 of Product Charter		Doc
SRS1	14	NS			8	174	Complete Section 1 of System Requirements Specification		Doc
SRS2	15	NS			5	179	Complete Section 2 of System Requirements Specification		Doc
SRS3	16	NS			13	192	Complete Section 3 of System Requirements Specification		Doc
SRS4	17	NS			5	197	Complete Section 4 of System Requirements Specification		Doc
SRS5	18	NS			8	205	Complete Section 5 of System Requirements Specification		Doc
SRS6	19	NS			8	213	Complete Section 6 of System Requirements Specification		Doc
SRS7	20	NS			13	226	Complete Section 7 of System Requirements Specification		Doc
SRS8	21	NS			21	247	Complete Section 8 of System Requirements Specification		Doc
SRS9	22	NS			13	260	Complete Section 9 of System Requirements Specification		Doc
	23	NS			13	273
	24	NS			8	281
	25	NS			8	289
	26	NS			8	297
	27	NS			13	310
	28	NS			21	331
	29	NS			13	344
	30	NS			8	352
	31	NS			8	360
	32	NS			21	381
Product Backlog Burn Chart
Features Remaining at Start of Sprint
Sprints

## Sprint_01_Backlog
Sprint #	1
Start on	7/1/19 12:00 AM
End on	7/7/19 12:00 AM
Demo on

Total Tasks	13
Day 1 Left	9
Day 2 Left	9
Day 3 Left	9
Day 4 Left	3
Day 5 Left	3
Day 6 Left	3
Day 7 Left	0

Task ID	Feature ID	Category	Type	Assigned To	Description	Status	Notes
1	Section 1	Project Charter		Jacob Wilkins
2	Section 2	Project Charter		Jacob Wilkins
3	Section 3	Project Charter		Jacob Wilkins
4	Section 4	Project Charter		Alex Mejia
5	Section 5	Project Charter		Alex Mejia
6	Section 6	Project Charter		Umanga Shrestha
7	Section 7	Project Charter		Sirjan Khanal
8	Section 8	Project Charter		Umanga Shrestha
9	Section 9	Project Charter		Sirjan Khanal
10	Section 10	Project Charter		Zohar Moreno
11	Section 11	Project Charter		Zohar Moreno
12	Section 12	Project Charter		Umanga Shrestha
13	Section 13	Project Charter		Everyone
Sprint Burn Chart
Days
Tasks